## Project Timesheet
Project Timesheet & Client Billing Log — India 2027
Log hours by task; billable amounts, cumulative hours and budget variance calculate in INR.
Project Name | Alpha Redesign |  |  | Budgeted Hours | 500
Client Name | Acme Corp |  |  | Actual Logged Hours | 25
Sprint / Phase | Sprint 4 |  |  | Billable Hours | 23
Project Manager | Priya Sharma |  |  | Total Billable (INR) | 32100
Default Rate (INR / hr) | 1500 |  |  | Hours Remaining (Budget − Actual) | 475
|  |  |  | Budget Used | 5%
Task ID | Sprint / Phase | Task Description | Developer / Resource | Date Logged | Hours Logged | Billable? (Yes/No) | Billable Rate (INR/hr) | Billable Amount (INR) | Cumulative Hours | Status / Remarks
TSK-101 | Sprint 4 | Backend API | Rajesh Kumar | 2027-01-11 | 8 | Yes |  | 12000 | 8 | Completed
TSK-102 | Sprint 4 | DB migration | Rajesh Kumar | 2027-01-12 | 4 | Yes |  | 6000 | 12 | Completed
TSK-103 | Sprint 4 | UI wireframes | Anita Rao | 2027-01-12 | 8 | Yes | 1200 | 9600 | 20 | In Progress
TSK-104 | Sprint 4 | Code review | Anil Gupta | 2027-01-13 | 3 | Yes |  | 4500 | 23 | In Progress
TSK-105 | Sprint 4 | Internal sprint retro | Team | 2027-01-15 | 2 | No |  | 0 | 25 | Non-billable
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on B8: Used when a row's own rate is left blank.

## How to use
How to use this template
Fill in the shaded cells
Shaded (light yellow) cells are inputs: project details, default rate, budgeted hours, and one row per task log.
Billable Amount = Hours × rate, only when Billable? is Yes. Leave a row's rate blank to use the default rate.
Cumulative Hours, totals, hours remaining and budget used are formulas.
The first rows are example entries. Overwrite or delete them before you start.
Invoicing
Amounts are in INR and exclude GST. Add GST on your invoice as applicable.
Free template from TrackPM — https://trackpm.com/blogs/free-timesheet-template-india/